## Product Backlog
Product Name:	C1325 Library Management System
Team ID:

Name:	Brandt Frazier
Initials:	BF
Student ID:	1000550249

(Additional names for teams only)
Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Total Features	27
Sprint 1 Left	17
Sprint 2 Left	8
Sprint 3 Left	8
				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Prio	Status	Sprint #	As a...	I want to...	So that...	Notes
AP	1	Complete	1	LIB	Add a publication	I can keep track of what is in the library
LP	2	Complete	1	LIB	List all publications	I can find out what is in the library	This will also be needed for the next two features
CO	3	Complete	1	LIB	Check out a publication	I can track who has borrowed each publication	Each publication will need to know if it is checked out or not
CI	4	Complete	1	LIB	Check in a publication	I can tell when a publication is returned
HE	5	Complete	1	LIB	Get help	I can learn how to use the system
SDM	6	Complete	2	LIB	Use a standard dialog for the main menu	I can interact more naturally with the system
SDP	7	Complete	2	LIB	Use a series of dialogs for a new publication	I can interact more naturally with the system
SDL	8	Complete	2	LIB	Use a stand dialog for the list of publications	I can interact more naturally with the system
SDH	9	Complete	2	LIB	Use dialogs for all other interaction (e.g., help)	I can interact more naturally with the system
SDC	10	Complete	2	LIB	Use dialogs for check in and check out	I can interact more naturally with the system
PA	11	Complete	2	LIB	Add a patron	I can conveniently keep track of all patrons	This is the Bonus level
SP	12	Complete	2	LIB	Select a patron when checking out a pub	I don't have to rekey recurring patron info	This is the Bonus level
SDA	13	Complete	2	LIB	Use dialogs for adding a new patron	I can interact more naturally with the system	Only required if the bonus level is implemented in time for Sprint #2
SDQ	14	Complete	2	LIB	Use a standard dialog for the list of patrons	I can interact more naturally with the system	Only required if the bonus level is implemented in time for Sprint #2
TI	15	NS		LIB	Add titles and icons to all dialogs	Improve the aesthetics of the system	This is the Sprint #2 Bonus level
CU	16	NS		LIB	Provide a custom dialog for new pubs	I can keep better track of library assets	This is the Sprint #2 Extreme Bonus level
CU	17	NS		LIB	Add custom info for each publication type	I can keep better track of library assets	This is the Sprint #1 Extreme Bonus level
SDM	6	NS	3	LIB	Use a menu bar in a main window for navigation	I can interact even more naturally with the system
TB	16	NS	3	LIB	Add a tool bar with buttons for the top 5 features	I can click once to initiate each action	This is the Sprint #3 Bonus level
TAB	17	NS	3	LIB	Add a table below the tool bar listing publications	I can quickly scroll through inventory	This is the Sprint #3 Extreme Bonus level
SRT	18	NS	3	LIB	Enable sorting by any column in the table	I can organize the table to task	This is the Sprint #3 Extreme Bonus level for additional points
FLT	19	NS	3	LIB	Enable filtering of the table by any text	I can quickly locate publications in a long list	This is the Sprint #3 Extreme Bonus level for ludicrous additional points
Product Backlog Burn Chart
Sprints
Features Remaining at Start of Sprint

## Sprint 01 Backlog
Sprint #	1				*** Create a new Sprint Backlog for EVERY SPRINT ***
Start on	Feb 14
End on	Feb 20
Demo on	TBD

Total Tasks	11
Day 1 Left	11
Day 2 Left	11
Day 3 Left	11
Day 4 Left	11
Day 5 Left	11
Day 6 Left	4
Day 7 Left	4

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
CON	SDM		code	Brandt	Use a standard dialog for the main menu	Complete
	SDP		code	Brandt	Use a series of dialogs for a new publication	Complete
TS	SDL		code	Brandt	Use a stand dialog for the list of publications	Complete
	SDH		code	Brandt	Use dialogs for all other interaction (e.g., help)	Complete
ICO	SDC		code	Brandt	Use dialogs for check in and check out	Complete
	PA		code	Brandt	Add a patron	NS
CO	SP		code	Brandt	Select a patron when checking out a pub	NS
	SDA		code	Brandt	Use dialogs for adding a new patron	Complete
CI	SDQ		code	Brandt	Use a standard dialog for the list of patrons	Complete
	CU		code	Brandt	Provide a custom dialog for new pubs	NS
	CU		code	Brandt	Add custom info for each publication type	NS
Sprint Burn Chart
Day
Tasks remaining

## Sprint 02 Backlog
Sprint #	1				*** Create a new Sprint Backlog for EVERY SPRINT ***
Start on	Feb 14
End on	Feb 20
Demo on	TBD

Total Tasks	12
Day 1 Left	12
Day 2 Left	12
Day 3 Left	12
Day 4 Left	12
Day 5 Left	12
Day 6 Left	3
Day 7 Left	3

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
	SDM		code	Brandt	Use a standard dialog for the main menu	Complete
	SDP		code	Brandt	Use a series of dialogs for a new publication	Complete
	SDL		code	Brandt	Use a stand dialog for the list of publications	Complete
	SDH		code	Brandt	Use dialogs for all other interaction (e.g., help)	Complete
	SDC		code	Brandt	Use dialogs for check in and check out	Complete
	PA		code	Brandt	Add a patron	Complete
	SP		code	Brandt	Select a patron when checking out a pub	Complete
	SDA		code	Brandt	Use dialogs for adding a new patron	Complete
	SDQ		code	Brandt	Use a standard dialog for the list of patrons	Complete
	TI		code	Brandt	Add titles and icons to all dialogs	NS
	CU		code	Brandt	Provide a custom dialog for new pubs	NS
	CU		code	Brandt	Add custom info for each publication type	NS
Sprint Burn Chart
Day
Tasks remaining

## Sprint 03 Backlog
Sprint #	1				*** Create a new Sprint Backlog for EVERY SPRINT ***
Start on	Feb 14
End on	Feb 20
Demo on	TBD

Total Tasks	12
Day 1 Left	12
Day 2 Left	12
Day 3 Left	12
Day 4 Left	12
Day 5 Left	12
Day 6 Left	3
Day 7 Left	3

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
				Brandt
				Brandt
				Brandt
				Brandt
				Brandt
				Brandt
				Brandt
				Brandt
				Brandt
				Brandt
				Brandt
				Brandt
Sprint Burn Chart
Day
Tasks remaining